## Template
Submission Date | OPDIV | UUID | System Name or Program Level | Weakness ID | Weakness Description | Identified Date | Weakness Creation Date | Scheduled Completion Date | Estimated Completion Date | Actual Completion Date | Source Type | Source Name | Source Detail | Source Document Date | Source ID | POC Contact Info | POC Role | Security Control | Severity | Risk | Status | $$ Resource Requirements | Resource Requirements (Hours) | Existing or New Funding | Comments | Recommended Remediation/ Milestones | Milestone POC | Milestone Scheduled Completion Date | Milestone Estimated Completion Date | Milestone Actual Completion Date | ISSO Responsible for Review
THE FIELDS BELOW IDENTIFY WHO COMPLETES THE INFORMATION. REFER TO THE 'DOCUMENATION TAB' FOR ADDITIONAL GUIDANCE ON THE FIELDS. | [15 empty] | This must be a Federal employee, not a contractor. | [5 empty] | At least one of these fields must be completed. Complete either Column W or X.
To be filled in by Audit Response & Coordination Team (ARC) | IHS | To be filled in by ISSO/Assessor | To be filled in by ISSO/Assessor | To be filled in by ARC | To be filled in by ISSO/Assessor | To be filled in by ISSO/Assessor | To be filled in by ARC | To be filled in by ISSO/Assessor | N/A | TBD | To be filled in by ISSO/Assessor | To be filled in by ISSO/Assessor | N/A | To be filled in by ISSO/Assessor | N/A | To be filled in by ISSO/Assessor | To be filled in by ISSO/Assessor | To be filled in by ISSO/Assessor | To be filled in by ISSO/Assessor | To be filled in by ISSO/Assessor | Ongoing | To be filled in by ISSO/Assessor | To be filled in by ISSO/Assessor | To be filled in by ISSO/Assessor | To be filled in by ISSO/Assessor. Include date and your initials. | To be filled in by ISSO/Assessor | To be filled in by ISSO/Assessor | To be filled in by ISSO/Assessor | To be filled in by ISSO/Assessor | TBD | TBD
BELOW IS AN EXAMPLE OF A SYSTEM LEVEL WEAKNESS:
2016-08-01 | IHS | 89221F7-B290-472B-9E10-EF2B7B186R5N | Widget Counting System | IHS_HQ_WCS_2016_Q4_01 | There is no comprehensive list of all hardware assets that should be included in the Widget Counting System authorization boundary. The hardware inventory should include the IP address, hostname, OS, OS version, location, etc. | 2016-07-04 | 2016-07-15 | 2017-10-31 |  |  | Security Control Assessment | WCS SAR FY2016 |  | 2016-06-17 |  | Joe Smith, joe.smith@ihs.gov | ISSO | CM-8 | Weakness | Moderate | Ongoing |  | 40 | Existing | I will work with Jen, Terry, and Lisa to identify all assets and run necessary scripts to export associated data for the inventory. 7/5/2016- JS. | 1. Identify all hosts that are included in this system. 2. Run scan to identify all required information about hosts. 3. Populate the Widget Counting System SSP. | 1. Joe (ISSO) and Jen (System Admin) 2. Joe (ISSO) 3. Joe (ISSO) | 1. 8/15/2015 2. 9/15/2015 3. 10/15/2015
#REF! | AHRQ | 18998787-E240-49CB-924D-BBBD223AD540 | AHRQ HCUP System | HCUP_2014-04-03_11 | DNSSEC is not implemented. | 2014-04-02 | 2014-04-30 | 2014-05-02 | 2014-05-02 | 2014-05-02 | AHRQ Risk Assessment | Risk Assessment for the Healthcare Cost and Utilization Project (HCUP) | Observation T-SC-21 (Page 15) | 2014-04-02 | T-SC-21 | Tae Kim tae.kim@truvenhealth.com 805-979-3735 | HCUP Security Manager | SC-21 | Weakness | Low | Complete | n/a | n/a | n/a | The HCUP System is an internal facing system without direct access from external sources. The servers hosting data do not have incoming or outgoing access to the internet (port 80/443 is blocked). Therefore, the risk of a man-in-the-middle attack is low since it would require the attacker to breach the Truven Health firewall (in addition to going undetected to various types of monitoring) to gain access to internal DNS servers. Complete (refer to risk acceptance waiver signed 5/2/2014)
#REF! | AHRQ | 18998787-E240-49CB-924D-BBBD223AD540 | AHRQ HCUP System | HCUP_2014-04-25_01 | Backup restore procedures not fully documented in the Contingency Plan. | 2014-04-25 | 2014-04-30 | 2014-07-01 | 2014-07-01 | 2014-06-27 | System Test and Evaluation | HCUP Database Servers Security Test and Evaluation (ST&E) | Appendix A - CP-10 (Page 99) | 2014-04-29 | CP-10 | Tae Kim tae.kim@truvenhealth.com 805-979-3735 | HCUP Security Manager | CP-10 | Weakness | Low | Complete | 1200 | 10 hours | new funding required from AHRQ | Procedures will be documented and included as part of the HCUP Contingency Plan.
Note on S1: DHHS: Family (dash) Number e.g. AC-3
Note on T1: HHS: Significant Deficiency Reportable Condition Weakness
Note on U1: HHS: High Moderate Low
Note on V1: HHS: Draft Ongoing Delayed Verification Complete Waivered

## Documentation
Weakness Template
Template Column | Reporting Field | Data Format/ Response Type | Field Description
A | Submission Date | Autofill | This will be the last day of the reporting cycle (e.g. 10/31/2011 or 11/15/2011). The first column autofills as rows are added.
B | OPDIV | Autofill | The second column autofills as rows are added.
C | UUID | 36 Char | finding
D | System Name | 255 Char | The System Name will be used as a validation point for the UUID. A program level finding are weaknesses that are pervasive; such as lack of policies. These are not tied to any particular system.
E | Weakness ID | 255 Char | This is the ID that has been assigned to the weakness. It must be unique within the OPDIV.
F | Weakness Description | 4000 Char | The description of the weakness.
G | Identified Date | MM/DD/YYYY | The date that the weakness was identified.
H | Creation Date | MM/DD/YYYY | The date that the weakness was entered into the POA&M.
I | Scheduled Completion Date | MM/DD/YYYY | The date committed to by the System Owner by which the weakness will be remediated. This is required by FISMA and cannot change once it has been entered.
J | Estimated Completion Date | MM/DD/YYYY | The current estimated date of completion.
K | Actual Completion Date | MM/DD/YYYY | The date upon which the weakness is closed.
L | Source Type | 255 Char | Type of source (audit, risk assessment, ST&E, SCA, response to an incident, other) by which the weakness was identified.
M | Source Name | 100 Char | Weakness source name (e.g., document title).
N | Source Detail | 1000 Char | Additional information about the source (e.g., page and paragraph).
O | Source Document Date | MM/DD/YYYY | Date of the source document.
P | Source ID | 36 Char | A unique Identifier assigned to the finding.
Q | POC Contact Info | 255 Char | Name and email of the point of contact for this weakness.
R | POC Role | 255 Char | Role of the Weakness POC.
S | Security Control Number | 36 Char | NIST SP 800-53 Security Control Family and Number (e.g., AC-3). Or reference FISCAM controls for A-123 weaknesses.
T | Severity | 36 Char | The weakness severity designation mandated by OMB and HHS Policy. Valid values are: "Significant Deficiency" - A weakness that drastically restricts the capability of the Department or OPDIV to carry out its mission or if it compromises the security of its information, information systems, personnel, or other resources, operations, or assets. In this context, the risk is great enough that the Department or OPDIV head and outside agencies must be notified, and immediate or near-immediate corrective action must be taken. "Reportable Condition"- A weakness that does not rise to the level of significant deficiency yet is still important enough to be reported to internal management. A security weakness that affects the efficiency and effectiveness of Department or OPDIV operations may be considered a reportable condition. Due to its lower associated risk, corrective actions for a reportable condition may be scheduled over a longer period of time. "Weakness" - All other weaknesses that do not rise to the level of a significant deficiency or reportable condition should be categorized as a weakness and mitigated timely and efficiently, as resources permit.
U | Risk | 36 Char | Risk assigned to the weakness for prioritization. Valid values are "High", "Moderate," and "Low".
V | Status | 36 Char | Status of the weakness in its remediation lifecycle. Valid values include "Draft", "Ongoing", "Delayed", "Verification", "Complete" and "Waivered".
W | $$ Resources Requirements | 255 Char | The monetary resources required to successfully complete the weakness (in dollars). One or both of the "Resource Requirements" fields must be populated.
X | Time Resource Requirements | 255 Char | The staff/contractor resources required to successfully complete the weakness (in hours). One or both of the "Resource Requirements" fields must be populated.
Y | Existing or New Funding | 36 Char | New or existing funding designation.
Z | Comments | 4000 Char | Detailed comments reflecting progress towards weakness closure.

## List
Severity | Risk | Status | Funding
Significant Deficiency | High | Ongoing | New
Reportable Condition | Moderate | Delayed | Existing
Weakness | Low | Completed