## EPCS Implementation Check List
EPCS Implementation Steps | User Role | Notes | Completed (Y/N)
Site/Facility
Area
Before Installation
1. Will your site use USB Cryptographic tokens for 2FA/Digital signing for all or some users? | N/A | – If yes: See sections 2.1, 2.2, 2.3, and 2.4 of the Token Provisioning Guide (bepc010o_EPCS_Token_Provisioning_Guide). – If only using PIV, skip to step 2. – If using USB Cryptographic token for some or all users, complete steps 1a through 1e.
1a. Determine which Credentialing Service Provider (IdenTrust or ORC) will be used. | Area/Site Acquisition Staff | See sections 2.1, 2.2, 2.3, and 2.4 of the Token Provisioning Guide (bepc010o_EPCS_Token_Provisioning_Guide). Note that the entire process can take several weeks.
1b. Purchase tokens. | Area/Site Acquisition Staff | This will be a different process based on whether tokens are acquired from ORC or IdenTrust. Follow the specific instructions for the vendor chosen in step 1a. For general guidance and helps, see sections 2.5, 4.0, and 5.0 of the Token Provisioning Guide (bepc010o_EPCS_Token_Provisioning_Guide).
1c. If the site purchases tokens and/or vouchers, distribute to the users. | Area/Site Acquisition Staff | See section 2.5.1 of the Token Provisioning Guide (bepc010o_EPCS_Token_Provisioning_Guide): Detailed instructions for procuring USB tokens, including web links and prices, are provided in sections 4.0 (IdenTrust) and 5.0 (ORC) of this document. If tokens or vouchers were purchased by the area's or site's acquisition team, the tokens or vouchers will need to be distributed to the users. – The vendors for cryptographic tokens will provide generic documentation that outline how individuals acquire a cryptographic token.To assist providers with setting up tokens, each site should consider modifying or augmenting the generic documentation with additional information, such as site-specific contacts, a site-specific URL provided by the portal, site branding, and any other site-specific information. – As all tokens are identical in appearance, each site should consider labelling the tokens in some manner (e.g., affixing a label or using a permanent marker) to identify the provider to whom the token belongs.
1d. Users go through identity proofing and acquire certificates. | Individual Users | See section 2.5.2 of the Token Provisioning Guide (bepc010o_EPCS_Token_Provisioning_Guide): USB tokens do not initially contain any certificates. After identity proofing, the signing certificate is provided by the vendor. Like the purchasing of tokens, the process of identity proofing, obtaining certificates, and installing certificates is also vendor specific. This information should be provided by the vendor when the tokens are purchased. See sections 4.0 (IdenTrust) and 5.0 (ORC) of this document for more information.
1e. Prepare workstations for USB token use. | Site Manager | See section 2.5.3 of the Token Provisioning Guide (bepc010o_EPCS_Token_Provisioning_Guide): This does not need to be done by individual users but will need to be done by site administrators to prepare the workstations that will either provision and/or will read the tokens. – Obtain and Install the Certificate Authority Trust Anchor – Prepare Workstations to read from a USB Token – Install HID ActivClient software The process to complete these items is documented in section 6.0.
1f. Users load certificates onto tokens. | Individual Users | This is based on whether tokens are acquired from ORC or IdenTrust. Follow the specific instructions for the vendor chosen in Step 1a of this worksheet. For more information, see section 2.5.4 of the Token Provisioning Guide (bepc010o_EPCS_Token_Provisioning_Guide).
2. Complete the Capacity Planning Spreadsheet | Site Manager | The EPCS Capacity Plan Spreadsheet is labeled bepc010o_EPCS_Capacity_Planning_Spreadsheet.xlsx. At minimum, complete the Base Capacity, Disk Capacity, and Backup Capacity worksheets, then review the thresholds associated with disk capacity and backup capacity.
3. Ensure patient addresses are being populated at patient registration. | Patient Registration Team | See section 3.6 of the EPCS Configuration Guide (bepc010o_EPCS_Configuration_Guide): All patients must have a mailing address for controlled substance prescriptions. If the patient does not have a mailing address on file, an error message will appear and the controlled substance cannot be ordered. This can be handled on a case-by-case basis, but if it is known that your site is missing the mailing address for many patients, the registration team should try to rectify as many of them as possible prior to implementation of EPCS.
4. Verify that the BSTS application is receiving updates from the DTS server. | Site Manager | See Section 3.8 of the EPCS Configuration Guide (bepc010o_EPCS_Configuration_Guide): As EPCS relies on updates from the DTS server, verify that BSTS application is communicating with and receiving updates from the DTS server.
5. Review and update providers |  | See section 3.1 of the EPCS Installation Guide (bepc010i): • All providers who will order controlled substances need a Department of Veterans Affairs (VA) number or a DEA number with a valid DEA Expiration Date. Prior to installation, sites should validate the DEA Number, DEA Expiration Date, and VA numbers for all internal providers to prevent failed orders.. • The DEA schedules assigned to internal provider should be checked for accuracy.
6. Update Quick Orders | CAC/Informaticist | See section 3.1 of the EPCS Installation Guide (bepc010i): If your site has quick orders setup for providers to dispense take-home medications after hours, validate that these quick orders are setup with pickup location equal to ‘Clinic’to prevent triggering Hardcopy prescription prompt in Pharmacy package
7. Cleanup Drug File | CAC/Informaticist | See section 3.1 of the EPCS Installation Guide (bepc010i): Make sure all controlled substances have the correct NDC and DEA Schedule entered in the DRUG file and have been properly matched to the NATIONAL DRUG FILE.
8. Install prerequisite patches. | Site Manager | Prerequisite Patches: HL7 Version 1.6 Patch 1006, BUSA Version 1.0, Kernel Version 8.0 Patch 1018, EHR Version 1.1 Patch 24, APSP Version 1.1 Patch 22, AVA Version 93.2 Patch 24, PSD Version 3.0 Patch 67, FileMan Version 22: If your site has one or more ePrescribing Ensemble namespaces and is currently a participating member of the IHS ePrescribing network that sends transmissions to Surescripts, BEPR Version 2.0 is also a prerequisite patch. For additional information, see the Patch Notes for each release and section 2.2 (Package Requirements) of the EPCS Install Guide (bepc010i).
7. Review training materials and documentation. | All staff that will use EPCS
Installation
1. Install all EPCS software. | Site Manager or Area Office | See the EPCS Install Guide (bepc010i) for information on pre-installation, installation order, and post-installation items. Also see the Patch notes for each release.
2. Assign the PSDRPH key. | Site Manager | See sections 3.2.6 and 6.1 of the EPCS Configuration Guide (bepc010o_EPCS_Configuration_Guide): The PSDRPH key is needed to finish and verify controlled substance orders. It should not be handed out liberally and is intended for pharmacists only. Users without the key cannot finish, edit, or change any controlled substance orders. They also will not be able to verify prescriptions.
3. Set up the parameters that have an immediate impact on Pharmacy processing. | CAC/Informaticist
3a. APSP CS II ORDER DATE MAX parameter | CAC/Informaticist | See section 7.4 of the EPCS Configuration Guide (bepc010o_EPCS_Configuration_Guide): This parameter holds the number of days after the issue date or the earliest fill date (if available) that a C-II order can continue to be processed. There is no default and the maximum value is 365 days. This parameter may be set at the division or system levels. If the pending order is older than this value the pharmacy is not able to process the order and it must be discontinued.
3b. APSP CS II RX EXPIRE DAYS parameter | CAC/Informaticist | See section 7.5 of the EPCS Configuration Guide (bepc010o_EPCS_Configuration_Guide): This parameter holds the number of days before a C-II prescription will expire. There is no default value and the maximum value is 365 days. This parameter can be set at the division and system levels.
Final Configuration to Enable EPCS (this steps should be done in conjunction with the EPCS Deployment and Implementation Team)
1. Configure the EPCS Monitoring Service. | Site Manager | See sections 4.1 and 4.2 of the EPCS Configuration Guide (bepc010o_EPCS_Configuration_Guide)
2. For sites outside of the IHS Intranet, configure the firewall. | Site Manager and Networking team | The IHS Network Operations and Security Center (NOSC) has adjusted the firewall/proxy rules for the IHS Intranet, so any RPMS site that is behind the IHS Intranet should not need to configure their firewall. For sites outside of the IHS Intranet, see section 4.3 of the EPCS Configuration Guide (bepc010o_EPCS_Configuration_Guide).
3. Add Credentialing Component to appropriate EHR Template(s). | CAC/Informaticist | See section 5.1.1 of the EPCS Configuration Guide (bepc010o_EPCS_Configuration_Guide).
4. Set up users to have the Provider Profile Administrator and Provider Access Administrator roles. | Site Manager | See section 5.1.2 of the EPCS Configuration Guide (bepc010o_EPCS_Configuration_Guide).
5. Complete the setup of users in the Provider Profile Administrator role | Site Manager and/or Provider Access Administrators | See section 3.2 of the EHR Patch 25 Supplemental User Guide (ehr_0110.25o_EPCS_Supplemental_User_Guide).
6. Enable Providers for EPCS | Provider Profile Administrators and Provider Access Administrators | See sections 3.3 – 3.8 of the EHR Patch 25 Supplemental User Guide (ehr_0110.25o_EPCS_Supplemental_User_Guide).
7. Assign the BEHOZMENU key. | Site Manager | See section 3.2.1 of the EPCS Configuration Guide (bepc010o_EPCS_Configuration_Guide): This key gives access to the IHS EPCS Main Menu, which holds the EPCS reports and configuration options and is a submenu to the existing RPMS-EHR Configuration Master Menu. See the EPCS Menus and Options section (of the EPCS Configuration Guide) for more information on the new EPCS options and how to access them.
8. Assign the BEHOZEPCSREPORT key. | Site Manager | See section 3.2.2 of the EPCS Configuration Guide (bepc010o_EPCS_Configuration_Guide): This key will enable access to many of the EPCS reports that are on available on the submenus under the IHS EPCS Main Menu. See the EPCS Menus and Options section (of the EPCS Configuration Guide) for more information on EPCS reports.
9. Assign the OREPCSSITE key. | Site Manager | See section 3.2.3 of the EPCS Configuration Guide (bepc010o_EPCS_Configuration_Guide): This key will allow the user to run two of the EPCS configuration options: the option that enables and disables EPCS for the site (Section 3.4) and the option that allow edits to the threshold values that impact the incident reports (Section 9.1.3.2). This key should be given user(s) that do RPMS configuration activities.
10. Add users to the BEHO EPCS Incident Response mail group. | Site Manager | See section 3.3 of the EPCS Configuration Guide (bepc010o_EPCS_Configuration_Guide): MailMan must be setup and active at the site as EPCS notifications will be communicated to providers and site administrators through MailMan messages. If the site is not currently using MailMan, please see the MailMan documentation for set-up instructions. EPCS created the BEHO EPCS Incident Response to receive notifications of possible security incidents, including tampered orders. This group will need to have members identified and assigned.
11. Verify the facility address and DEA Number. | Site Manager | See section 3.5 of the EPCS Configuration Guide (bepc010o_EPCS_Configuration_Guide): Ensure that the main facility has an address defined in the Institution (#4) file. The facility address is used as the provider address for the order and is required for every controlled substance order. If you plan to send controlled substance orders to Surescripts, the address cannot be a post office (PO) box. Along with the address, the facility DEA number and expiration date must be defined. A MailMan message will be generated for users with the PSDRPH key thirty (30) days prior to expiration. If you plan to enable EPCS for multiple divisions, you will need to setup the facility address and DEA number for each division that will be enabled.
12. Setup EPCS TaskMan jobs. | Site Manager | See section 3.7 of the EPCS Configuration Guide (bepc010o_EPCS_Configuration_Guide): There are two processes that must be tasked to run periodically in order to meet DEA requirements. – BEHO EPCS Audit Summary Task: This option generates a daily incident report that will be sent to the BEHO EPCS Incident Response mail group. Per DEA requirements, it must be scheduled to run daily. This task will be automatically scheduled at 2:00 AM. Please validate that this is scheduled, and if it is not, schedule the process to run daily. OR EPCS CS RX By Provider: This option generates a list of CS prescription created by each provider and, per DEA requirements, should be scheduled to run before the seventh day of every month. This task will be automatically scheduled at 9:00 PM on the first day of the month. Please validate that this is scheduled, and if it is not, schedule the process to run monthly.
13. Set up the parameters that impact EPCS. | CAC/Informaticist | See section 7.0 of the EPCS Configuration Guide (bepc010o_EPCS_Configuration_Guide).
13a. AUTO RX SCHEDULE RESTRICT parameter | CAC/Informaticist | See section 7.1 of the EPCS Configuration Guide (bepc010o_EPCS_Configuration_Guide): This parameter controls which schedules can be transmitted through Surescripts.It should only be edited after the site is approved for Surescripts transmission. This parameter should at least include 1, as schedule 1 drugs may not be prescribed by law.
13b. APSP AUTO RX CII PRESCRIBING parameter | CAC/Informaticist | See section 7.2 of the EPCS Configuration Guide (bepc010o_EPCS_Configuration_Guide): This parameter controls whether a site can create C-II orders in the EHR for internal or external pharmacies. It is an existing parameter but should be reviewed after EPCS is installed.
13c. APSP AUTO RX ERX OF CSII parameter | CAC/Informaticist | See section 7.3 of the EPCS Configuration Guide (bepc010o_EPCS_Configuration_Guide): This parameter controls whether a site can send C-II orders to Surescripts.It is an existing parameter but was not editable prior to EPCS. This parameter should only be edited after the site is approved and configured for Surescripts, including approval for CS orders.
13d. BEHO EPCS CERT NAME THRESHOLD parameter | CAC/Informaticist | See section 7.6 of the EPCS Configuration Guide (bepc010o_EPCS_Configuration_Guide): The Credentialing application does a comparison of the user name in RPMS and the user name on the certificate that was entered for the user. When the names do not match, an alert is sent to EPCS Incident Response mailgroup. This parameter is used to set the number of character difference between the two names that will cause the alert to be generated. The default value is 3, with allowed values from 1 to 10.
13e. BEHORX REQUIRE SUPERVISOR CS parameter | CAC/Informaticist | See section 7.7 of the EPCS Configuration Guide (bepc010o_EPCS_Configuration_Guide): This parameter controls which TIU user classes will have a supervisor set and displayed for ordering controlled substance medications. The supervisor will display on printed prescriptions, when the prescription is being processed on in-house RXs, in the message to Surescripts, and when viewing a prescription Sites may use the existing user classes or create new ones as needed. This parameter can be set at the division and system levels.
13f. BEHORX ENABLE EARLIEST DATE parameter | CAC/Informaticist | See section 7.8 of the EPCS Configuration Guide (bepc010o_EPCS_Configuration_Guide): This parameter allows a site to enable the dialog box for earliest date. This can be set to YES in states that allow providers to order multiple C II narcotics at the same time provided that they indicate different start dates up to 90 days in the future. This parameter can be set at the division and system levels.
13g. BEHORX HARDCOPY AT SIGNING parameter | CAC/Informaticist | See section 7.9 of the EPCS Configuration Guide (bepc010o_EPCS_Configuration_Guide): This new parameter controls the availability of a checkbox in the eSig signing dialog when CS meds are present, and the user is EPCS enabled. The intention of this parameter is to set it for a user when there is a compelling reason for the provider to create a paper order for a CS Medication even though they are EPCS enabled (e.g., the user left their token at home or the user is locked out of their token), and then remove it when that reason is fulfilled or no longer applicable. This parameter is not intended to be set for all users for all time and may not be used when a user’s token is lost, stolen, or otherwise compromised. In these cases, the user's EPCS access should be revoked in the Credentialing Component of EHR. The parameter may be set at the system, division, and user levels, though it is strongly recommended to be set at the user level only.
13h. BEHORX MAX DAYS SUPPLY CS parameter | CAC/Informaticist | See section 7.10 of the EPCS Configuration Guide (bepc010o_EPCS_Configuration_Guide): This parameter allows a site to set the maximum days supply that can be ordered for controlled substance medications. Prescribers will not be able to save an order for CS medications that exceed the days entered for this parameter. The range is 1–180 days’ supply and definable for schedules 2 through 5. If a schedule is not defined, the max days’ supply will default to 30. This parameter can be set at the division and system levels.
13i. BEHORX PRINT FORMATS parameter | CAC/Informaticist | See section 7.11 of the EPCS Configuration Guide (bepc010o_EPCS_Configuration_Guide): The EPCS print formats should be selected as the default items.These defaults add required DEA data to any prints/reprints of prescriptions. This parameter can be set at the user, class, location, division, and system levels.
14. Setup Rx print formats required for EPCS. | CAC/Informaticist | See section 5.2 of the EPCS Configuration Guide (bepc010o_EPCS_Configuration_Guide).
15. Surescripts set up (if used). | Site Manager/Informaticists | See section 3.9 of the EPCS Configuration Guide (bepc010o_EPCS_Configuration_Guide): If a site is currently enabled to transmit prescription orders to Surescripts, two additional steps need to be done to enable EPCS for Surescripts: – Setup the AUTO RX SCHEDULE RESTRICT, APSP AUTO RX CII PRESCRIBING, and APSP AUTO RX ERX OF CS II parameters, which are documented in Section 7.0. – Work with the ePrescribing team to enable the site's prescribers with the Controlled Substance Service Level. If a site does not have ePrescribing currently enabled and would like to have it enabled, create a helpdesk ticket for the eRx team enable Surescripts. Note that this is not required prior to turning EPCS on (step 12 below).
16. Turn on EPCS for the site. | Site Manager | See section 3.4 of the EPCS Configuration Guide (bepc010o_EPCS_Configuration_Guide).
End